## Sheet1
Reversi - Product Backlog
ID | Description | Status | Sprint | Priority | Comments
1 | Server Code | Done | 1 |  |  | Iterations | Tasks Left
2 | Telnet to server | Done | 1 |  |  | 1 | 19
3 | Game board representation | Done | 1 |  |  | 2 | 7
4 | Game board print-out | Done | 1 |  |  | 3
5 | Game operator | Done | 1
6 | Operator Legality Checks | Done | 1
7 | Enable User Moves | Done | 1
8 | Win condition detection | Done | 1
9 | Undo/Redo | Done | 1
10 | Undo/Redo depth 10 | Planned | 1
11 | Indicated possible moves | Planned | 1
12 | Report win/losses | Planned | 1
13 | AI random guessing | Planned | 2
14 | AI min-max searching | Planned | 2
15 | AI alpha-beta-pruning based | Planned | 2
16 | More advanced AI/custom evaluation function | Planned | 2
17 | GUI display gameboard | Planned | 3
18 | GUI mouse click for move | Planned | 3
19 | Server connect to other servers | Planned | 3
Backlog based on Petri Heiramo's product and sprint backlog template found at: http://agilesoftwaredevelopment.com/2006/11/scrum-backlog-templates-and-examples
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on E4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.